## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: Web Development
INTERN NAME: Shreya Panse
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 20-May-2025
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | CollegeCompass — College Finder Web Application
PROJECT ID
INTERN NAME | Shreya Panse
PROJECT MANAGER | Harshada Topale
INTRODUCTION
CollegeCompass is a full stack web application built using HTML, CSS, JavaScript for the frontend and Node.js with Express.js for the backend, with a MySQL database. The application allows students across India to discover, filter and compare colleges based on their entrance exam percentile, domain of interest, college type, fees and placement data. This test plan covers functional testing of all API endpoints, frontend page interactions, filter and search behaviour, pagination, the compare feature and database integrity.
SCOPE
IN SCOPE: • Landing page load, animations and quiz navigation • College search and filter by exam, percentile, domain, type and country • Pagination — 20 colleges per page, page navigation • College detail page — cutoffs, placements, courses, campus data • College comparison — up to 3 colleges side by side • All REST API endpoints: GET /colleges, GET /colleges/:id, GET /colleges/exams/all, POST /colleges/compare • MySQL database — data integrity, foreign key relationships • Mobile responsiveness on screen widths below 900px • Cross-browser testing on Chrome and Edge
OUT OF SCOPE: • AI chatbot feature (not yet implemented) • User authentication and saved colleges feature (not yet implemented) • Cutoff prediction algorithm (planned, not yet implemented) • Performance load testing beyond 100 concurrent users • iOS and Android native app testing • Payment gateway or subscription features
QUALITY OBJECTIVE
Quality Objectives for CollegeCompass: • Ensure all API endpoints return correct and complete data matching the MySQL database • Ensure filters (exam, percentile, domain, type, country) return accurate filtered results • Ensure the compare feature correctly displays and highlights best values across colleges • Ensure the pagination system correctly divides results into pages of 20 • Ensure the college detail page renders all available data without layout breaks • Ensure no broken pages, console errors or failed API calls exist on any user flow • Ensure the application is usable on mobile screen widths (below 900px)
Some objectives of your testing project could be • Ensure the Application Under Test conforms to functional and non-functional requirements • Ensure the AUT meets the quality specifications defined by the client • Bugs/issues are identified and fixed before go live
ROLES AND RESPONSIBILITIES
Roles and Responsibilities: • Developer / QA Analyst (Shrey): Write and execute all test cases, log bugs, verify fixes, maintain test plan • Project Manager (Harshada Topale): Review test plan, approve test completion criteria, sign off • Domain Lead: Review coding standards compliance, validate API design against requirements
• QA Analyst • Test Manager • Configuration Manager • Developers • Installation Team Amongst others
TEST METHODOLOGY
OVERVIEW: The Agile methodology has been adopted for CollegeCompass. Since the project is developed iteratively — with features like search, filters, pagination and compare added phase by phase — Agile allows testing to happen alongside each development sprint. This ensures bugs are caught early before the next feature is built on top.
Selected Methodology: Agile Testing is performed at the end of each feature sprint: Sprint 1 — Backend API and database testing Sprint 2 — Frontend search and filter testing Sprint 3 — Pagination and compare feature testing Sprint 4 — Mobile responsiveness and cross-browser testing
TEST LEVELS: • Unit Testing: Individual API route handlers tested using browser and Postman • Integration Testing: Frontend fetch calls tested against live backend API • System Testing: Full end-to-end user flows tested in browser (search → detail → compare) • Regression Testing: All previously passing tests re-run after any code change
Primary testing level for this project: System Testing and Integration Testing. Given the solo developer context and sprint-based delivery, system testing of complete user flows is the most efficient and impactful level of testing for CollegeCompass.
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
Test Completeness Criteria for CollegeCompass: • All 15 planned test cases executed • All Priority 1 and Priority 2 bugs resolved and verified • All 4 API endpoints return correct responses verified in browser • Landing, Explore, Detail and Compare pages load without console errors • Filters (exam, percentile, domain, type) tested with valid and invalid inputs • Mobile layout verified at 375px and 768px widths
TEST DELIVERABLES
Test Deliverables for CollegeCompass: • Test Plan (this document) • Test Cases sheet (within this workbook) • Bug Report log • API endpoint verification screenshots • Final test sign-off from Project Manager
Here are the sample deliverables • Test Plan • Test Cases • Requirement Traceability Matrix • Bug Reports • Test Strategy • Test Metrics • Customer Sign Off
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
Testing Tools: • Browser DevTools (Chrome) — inspect API responses, console errors, network calls • Postman or REST Client (VS Code extension) — test API endpoints directly • MySQL Workbench — verify database data integrity • VS Code — code review and static analysis • GitHub — version control and code change tracking
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Following software’s are required in addition to client-specific software. • Windows 8 and above • Office 2013 and above • MS Exchange, etc.
ADDITIONAL COMMENTS
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Landing Page Load | Verify landing page loads with animations, hero section, exam ticker and feature cards visible | 20-May-2025 | 21-May-2025 | Shrey | Pass
API — GET /colleges | Verify API returns 20 colleges per page with correct pagination object (total, page, totalPages, hasNext, hasPrev) | 20-May-2025 | 21-May-2025 | Shrey | Pass | Tested via browser and Postman
API — GET /colleges/exams/all | Verify all 12 exams returned correctly from database | 20-May-2025 | 21-May-2025 | Shrey | Pass
API — GET /colleges/:id | Verify single college returns all nested data: placements, cutoffs, courses, factors | 20-May-2025 | 21-May-2025 | Shrey | Pass
API — POST /colleges/compare | Verify compare endpoint accepts 2-3 IDs and returns correct college data for each | 20-May-2025 | 21-May-2025 | Shrey | Pass
Filter — Exam | Select JEE Main chip — verify only colleges with JEE Main cutoffs returned | 21-May-2025 | 22-May-2025 | Shrey | Pass
Filter — Percentile | Enter percentile 99 — verify only colleges with cutoff range covering 99 returned | 21-May-2025 | 22-May-2025 | Shrey | Pass
Filter — Domain Medical | Select domain Medical — verify AIIMS and medical colleges appear, engineering colleges do not | 21-May-2025 | 22-May-2025 | Shrey | Pass | Fixed by adding college_courses links
Filter — College Type | Select IIT checkbox — verify only IIT type colleges returned | 21-May-2025 | 22-May-2025 | Shrey | Pass
Pagination | Verify page 1 shows 20 colleges, clicking Next loads page 2 with next 20, scrolls to top | 21-May-2025 | 22-May-2025 | Shrey | Pass
Search Bar | Type "IIT" in search bar — verify cards filter to IIT colleges only from current page | 22-May-2025 | 23-May-2025 | Shrey | Pass
College Detail Page | Click any college card — verify detail page loads with college name, cutoffs, placements, courses and campus data | 22-May-2025 | 23-May-2025 | Shrey | Pass
Compare Feature — Add | Click + Compare on 2 colleges — verify compare bar appears at bottom with both college names | 22-May-2025 | 23-May-2025 | Shrey | Pass
Compare Feature — Table | Click Compare Now — verify compare.html shows side-by-side table with best values highlighted in green | 22-May-2025 | 23-May-2025 | Shrey | Pass
Mobile Responsiveness | Open index.html at 375px width — verify sidebar hides, cards stack in single column, nav is usable | 23-May-2025 | 24-May-2025 | Shrey | In Progress | Mobile sidebar filter drawer pending
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.