## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: Web Development
INTERN NAME: Shreya Panse
PROJECT NAME: CollegeCompass
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2025-05-20
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | CollegeCompass — College Finder Web Application |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Industry Academia Community (IAC)
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 20-May-2025 | Express route ordering bug — GET /colleges/exams/all was being intercepted by the /:id wildcard route, returning a "college not found" error instead of the exam list. | Technical — Backend Development | Yes — endpoint returned a 404-style JSON error instead of exam data. Exam chips on the frontend failed to load. | In Express.js, routes are matched in the order they are declared. Specific named routes must always be placed above wildcard routes like /:id to prevent accidental matching. | Moved the /exams/all route declaration above the /:id route in colleges.js. Restarted server and verified all endpoints returned correct responses. | Shrey | Solved | This is a common Express.js pitfall. Future route files should follow the convention: specific routes first, wildcard routes last.
2 | 21-May-2025 | Medical domain filter returned 0 results despite 13 medical colleges existing in the colleges table. Students selecting Medical saw an empty college grid. | Technical — Database | Yes — domain filter returned 0 results immediately after medical colleges were inserted. Should have been flagged as a data integrity issue. | Every college inserted into the colleges table must also have corresponding records in the college_courses junction table. Without these links the JOIN-based domain filter cannot find the college regardless of its type. | Ran INSERT statements to link all medical, law, design and arts colleges to their respective courses in the college_courses table. Added this step to the data import checklist. | Shrey | Solved | All future college imports must include a college_courses insert step. A validation query should be run after every import to check for colleges with no course links.
3 | 22-May-2025 | MySQL LOAD DATA INFILE command failed with Error Code 1064 because "rank" is a reserved keyword in MySQL and cannot be used as a column name without backtick escaping. | Technical — Database | Yes — error message clearly stated syntax error near "rank". Should have been caught during query review. | Avoid using MySQL reserved keywords as column names. If unavoidable wrap column names in backticks. Alternatively use a Node.js import script instead of raw SQL LOAD DATA INFILE for better control and error handling. | Replaced the MySQL LOAD DATA INFILE approach with a custom Node.js import script using the fs and mysql2 modules. The script handles CSV parsing, duplicate detection and error logging more robustly than raw SQL. | Shrey | Solved | Node.js import scripts are more maintainable than raw SQL imports for CSV data. They allow custom transformation logic, progress logging and graceful error handling.
4 | 23-May-2025 | Pagination was resetting all applied filters when the user navigated to a different page. Page 2 showed unfiltered results even after the user had applied exam and domain filters. | Technical — Frontend Development | Yes — filter chips deactivated visually when changing pages. This was observable during manual testing. | Filter state must be stored in a persistent variable outside the loadColleges function. Using local variables inside async functions means state is lost between calls. | Created a global currentFilters object in JavaScript that stores the active filter values. The changePage() function now passes currentFilters to every loadColleges() call ensuring filters persist across all page navigations. | Shrey | Solved | State management is critical in multi-page frontend applications. Even without a framework like React, global state variables can effectively manage filter and pagination state.
5 | 23-May-2025 | College cards displayed "₹NaNL" for average package on colleges imported from the NIRF CSV which had no placement records in the placements table. | Technical — Frontend Development | Yes — NaN values were visible immediately when the explore page loaded with NIRF-imported colleges. | Always use null-safe checks before rendering data from API responses. Never assume all records will have all fields populated, especially when data comes from multiple sources of varying completeness. | Updated renderColleges() to use conditional rendering for all stat values. Empty or null values now display a clean dash "—" instead of undefined or NaN. Pattern: c.avg_package_lpa ? value : "—". | Shrey | Solved | Defensive rendering should be applied to all dynamic data fields from the start of frontend development, not added as a fix after bugs appear.
6 | 24-May-2025 | The .env file containing the database password was not added to .gitignore initially. It was caught before any GitHub push but could have led to credential exposure. | Technical — Security | Yes — .env file appeared in the VS Code source control panel as an untracked file ready to be committed. | Always create a .gitignore file at project initialisation before writing any code. Add node_modules, .env and any other sensitive files to .gitignore as the very first step of every new project. | Added .gitignore to the project root with entries for .env and node_modules/. Verified .env was no longer tracked by Git. Documented this as a required first step in the coding standards. | Shrey | Solved | Security best practices must be established at project setup not discovered reactively. This should be a standard checklist item for all future projects.
7 | 23-May-2025 | The NIRF ranking portal removed the CSV download button from their website. The expected direct download was unavailable requiring an alternative data source to be found. | Planning — Data Collection | Yes — the download button was missing from the page. Multiple page refreshes confirmed it was not a loading issue. | Always have a backup data source identified before beginning data collection. Government portals frequently change their interfaces. Kaggle and data.gov.in are reliable mirrors for NIRF and JoSAA data. | Found the NIRF 2024 dataset on Kaggle as a pre-compiled CSV. Downloaded and used this as the primary data source. Import script was written to match the Kaggle CSV column format. | Shrey | Solved | Official government data portals should not be the only planned data source. Always identify at least one alternative (Kaggle, data.gov.in, web scraping) before starting the project.
8 | 21-May-2025 | The NIRF CSV contained only college name, city, state, score and rank. It did not include fees, placement data or course information. These had to be sourced separately or estimated. | Planning — Data Quality | No — data completeness was not verified before planning the import strategy. | Before designing the database schema and import scripts, always inspect the source data files to understand what fields are actually available. Do not assume a dataset contains all required fields. | Fees were estimated by college type using publicly known ranges. Placement data was manually sourced and inserted for the top 20 seed colleges. A disclaimer was added to the application noting that estimated data is used where real data is unavailable. | Shrey | Pending | A data audit step should be added to the project planning phase of all future data-driven projects. Identify gaps before development begins not during.
9 | 20-May-2025 | The project scope was originally limited to IT and Management colleges as per the brief. During development it was expanded to include Medical, Law, Design and Arts colleges to make the platform more useful. | Planning — Scope Management | No — scope expansion was a deliberate and beneficial decision made during development. | Scope changes during development should be documented even when they are positive. Recording why a scope change was made helps future developers understand the project evolution and avoids confusion. | Documented the scope change in the Project Report under Objectives. Added Medical, Law, Design and Arts as supported domains. Updated the filter dropdown and database accordingly. | Shrey | Solved | Positive scope expansions are still scope changes and should be tracked. In future projects all scope changes should be logged in the RAID log as decisions with rationale.
10 | 25-May-2025 | Testing was performed manually throughout development rather than following a structured test plan from the beginning. Some bugs (like the medical filter issue) were discovered late. | Process — Testing | No — bugs were found during ad-hoc testing rather than through a defined test cycle. | Write the test plan before beginning frontend development, not after. Having predefined test cases ensures systematic coverage of all features and catches integration issues earlier in the development cycle. | Completed the Test Plan and Traceability Matrix as formal deliverables. For future sprints (chatbot, user accounts) test cases will be written alongside the feature design before coding begins. | Shrey | Solved | Test-driven thinking (writing expected results before writing code) would have caught the college_courses data gap earlier. This should be adopted in future sprints.
11 | 25-May-2025 | Using a Node.js import script instead of manual SQL inserts for bulk college data worked extremely well. The script imported 354 colleges in under 10 seconds with automatic duplicate detection. | Technical — Backend Development | N/A | Continue using automated import scripts for all future data loading tasks. Parameterised queries in Node.js are safer, faster and more maintainable than manual SQL inserts for large datasets. | Retained import.js as a reusable pattern. Will write import_cutoffs.js using the same approach for JoSAA cutoff data once the CSV is available. | Shrey | Solved | Automation of repetitive data tasks is always preferable to manual SQL. The script pattern can be reused for any future data import task with minimal modification.
12 | 24-May-2025 | Dark navy UI theme with green accent colors and card hover animations gave the application a professional and distinctive visual identity that stands out from typical student-facing websites. | Technical — Frontend Design | N/A | Continue using CSS custom properties (variables) for theming. They make global color changes trivial and ensure visual consistency across all pages. | All color values defined as CSS variables in :root. Animations implemented using CSS keyframes and cubic-bezier easing for smooth natural motion. | Shrey | Solved | Investing time in a cohesive design system at the start of frontend development pays off significantly. Consistent colors, spacing and animation timing created a polished final product.
13 | 22-May-2025 | Separating backend routes into a dedicated routes/colleges.js file from the beginning made the codebase much easier to navigate and maintain as new endpoints were added. | Technical — Code Organisation | N/A | Always separate route handlers from the main server.js file even for small projects. As the project grows, having separate route files for each domain (colleges, users, chat) prevents server.js from becoming unmanageable. | Maintained the routes/ folder structure throughout development. Will add routes/chat.js and routes/users.js as separate files when those features are built. | Shrey | Solved | Good project structure established early saves significant refactoring time later. The file structure conventions documented in the Coding Standards should be followed from day one of every project.
14 | 25-May-2025 | Using localStorage to persist the compare list across page navigations meant students could browse multiple pages and add colleges to their compare list without losing their selections. | Technical — Frontend Development | N/A | Use localStorage for lightweight client-side state that needs to persist across page navigation. For more complex state management in future sprints consider sessionStorage or a backend-stored user session. | compareList stored as JSON in localStorage. updateCompareBar() called after every add/remove operation to keep the UI in sync. A try-catch wrapper to be added to handle browsers with localStorage disabled. | Shrey | Solved | Client-side persistence using localStorage is a simple and effective solution for short-term user state. It requires no backend changes and works immediately across all pages.
15 | 25-May-2025 | The Agile sprint-based approach — building one complete feature at a time (setup → database → API → data → frontend → testing → documentation) — kept the project focused and delivered a working product at every stage. | Process — Project Management | N/A | Continue using sprint-based development for all future features. Define the feature, build the backend first, test the API, then build the frontend. This order prevents frontend work being blocked by incomplete APIs. | Applied the same backend-first approach to all features. Will continue this pattern for the chatbot sprint (build /chat API first, then build the chat widget UI). | Shrey | Solved | Backend-first development in an Agile model is highly effective for full stack projects. It ensures the data layer is solid before UI work begins and reduces rework caused by API changes after frontend is built.