## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | CollegeCompass — College Finder Web Application
PROJECT SPONSOR
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 20-May-2025
EXPECTED COMPLETION DATE | 25-May-2025
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To build a full stack web application that enables students across India and abroad to discover, filter and compare colleges based on their entrance exam percentile, domain of interest, college type, fees and placement data. The application consolidates data from 455 colleges across 6 domains (Engineering, Management, Medical, Law, Design, Arts) into a single searchable, filterable and comparable platform — replacing the need for students to visit multiple websites during college selection.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Every year over 1 million students appear for competitive entrance exams in India (JEE, CAT, NEET, CLAT etc.) and face a stressful, fragmented college selection process. They must visit the NIRF portal for rankings, the JoSAA portal for cutoffs, individual college websites for fees, and LinkedIn or Shiksha for placement data — none of which are connected. CollegeCompass solves this by providing a unified, free, data-driven platform where a student with a 94 percentile in JEE Main can instantly see every NIT they are eligible for, compare 3 colleges side by side across 13 metrics, and make an informed decision — all in under 5 minutes. This saves students hours of research and reduces dependence on paid counselling services.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Goal 1 — Functionality: Build a working full stack application with search, filter, pagination, detail and compare features. Target: All 4 API endpoints returning correct data. All 5 filter types working accurately. Goal 2 — Data Coverage: Import and store data for 455+ colleges across all 6 domains. Target: 455 colleges in database. 62+ colleges with verified placement data. Goal 3 — Performance: API responses under 500ms for paginated queries. Target: 20 colleges per page loaded in under 1 second on localhost. Goal 4 — Documentation: Complete all 8 required project documents. Target: Coding Standards, Test Plan, RTM, Project Report, Project Schedule, RAID Log, Lessons Learnt, SDS, Project Charter, Requirement Elicitation. Goal 5 — Code Quality: Follow all naming conventions and file structure rules defined in the Coding Standards document. Target: Zero deviations from documented conventions.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | 1. Working Web Application — landing.html, index.html, college.html and compare.html fully functional and connected to the Node.js backend API. 2. MySQL Database — college_finder database with 7 tables and 455 college records across 6 domains. 3. REST API — 4 documented endpoints with filtering, pagination and comparison support. 4. Data Import Scripts — import.js (NIRF CSV) and import_cutoffs.js (JoSAA CSV) for repeatable data refresh. 5. LP Coding Standards Document 6. Test Plan (15 test cases) 7. Requirement Traceability Matrix (30 test cases) 8. Project Report 9. Project Schedule 10. RAID Log (20 entries) 11. Lessons Learnt Log (15 lessons) 12. Software Design Specification 13. Requirement Elicitation Questionnaire 14. Project Charter (this document)
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | 1. College search by name and city using a debounced search bar. 2. Filter colleges by entrance exam (12 exams: JEE Main, JEE Advanced, CAT, NEET, BITSAT, CUET, GATE, SAT, IELTS, CLAT, NATA, UCEED). 3. Filter colleges by percentile range — returns only eligible colleges. 4. Filter colleges by domain: Engineering, Management, Medical, Law, Design, Arts. 5. Filter colleges by college type: IIT, NIT, IIIT, IIM, Deemed, Private, State, Abroad. 6. Filter colleges by country: India, Canada, Singapore, Australia, UK. 7. Sort results by NIRF rank, average package, fees and placement percentage. 8. Paginated results — 20 colleges per page with page navigation. 9. College detail page showing cutoffs, placements, courses and campus information. 10. Side-by-side comparison of up to 3 colleges across 13 metrics with best-value highlighting. 11. Animated landing page with hero section, exam ticker and feature cards. 12. All project documentation deliverables listed under Expected Deliverables. 13. Cross-browser compatibility on Chrome and Microsoft Edge. 14. Mobile-responsive layout (sidebar hidden, single-column cards at 900px and below).
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | 1. AI Chatbot — Claude API integration for natural language college queries. Deferred to future sprint. 2. User Authentication — register, login, saved college shortlists and profile pages. Deferred to future sprint. 3. Cutoff Prediction — linear regression model for predicting 2025 cutoffs from historical data. Deferred pending multi-year JoSAA CSV availability. 4. Mobile Filter Drawer — slide-up filter panel for mobile devices. Partially implemented; animation pending. 5. Admin Dashboard — web interface for non-technical data updates. Deferred to future sprint. 6. Production Deployment — deploying to Railway (backend), Netlify (frontend) and Supabase (database). Planned post-documentation sprint. 7. Email or push notifications for application deadlines. Requires user accounts — deferred. 8. JoSAA 2025 cutoff data — not yet available as counselling occurs in July 2025. 9. Payment gateway or subscription features — not applicable to this project. 10. iOS and Android native mobile application.
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | Intern / Full Stack Developer: Shrey — 1 resource Responsibilities: Database design, backend API development (Node.js + Express), frontend development (HTML/CSS/JS), data import scripts, testing and all project documentation. Estimated hours: 40–50 hours total across the project duration (20 May – 25 May 2025).
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Hardware: Windows laptop with minimum 8GB RAM (development and testing machine). Software (all free/open source): — Node.js v20 LTS (nodejs.org) — MySQL Server 8.0 (dev.mysql.com) — MySQL Workbench 8.0 (dev.mysql.com) — Visual Studio Code with ESLint, Prettier and REST Client extensions — Google Chrome and Microsoft Edge browsers — Git (version control) Data Sources (all free): — NIRF 2024 Rankings CSV (Kaggle) — JoSAA Cutoff CSV (Kaggle / josaa.nic.in) Future resources (planned): — Railway hosting account (free tier for backend deployment) — Netlify account (free tier for frontend deployment) — Anthropic API credits (for AI chatbot sprint)
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | All tools and resources used in this project are free and open source. There is no monetary cost associated with the development phase. Developer cost: IAC Internship Programme — no financial cost to the project. Hosting cost (current): INR 0 — application runs locally on development machine. Hosting cost (planned production): Railway free tier — INR 0/month up to usage limits. Data cost: NIRF and JoSAA CSVs sourced from Kaggle at no cost. API cost (future chatbot sprint): Anthropic Claude API — free trial credits available. Total estimated project cost: N/A (Internship project — no budget allocated)
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner)
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | .
END CUSTOMER (Mention the client name.) | Primary end customer: Students aged 17–25 across India who have appeared for competitive entrance exams and are in the process of selecting colleges for admission. Secondary customers: Parents and educational counsellors who assist students in the college selection process. Internal customer: Industry Academia Community (IAC) — receives the completed project and all documentation as the deliverable of the Live Project programme.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | R1 (High) — JoSAA 2025 cutoff data not available until July 2025. Application uses 2024 data with disclaimer. R2 (High) — Application not yet deployed to a public server. Accessible only on local machine. R3 (Moderate) — Only 62 of 455 colleges have verified placement data. Remaining colleges show blank placement fields. R4 (Moderate) — No input validation or rate limiting on API endpoints. Risk of malformed requests or server overload. R5 (Low) — localStorage unavailability in private browsing mode may affect the compare feature persistence. R6 (Closed) — .env file with DB credentials could have been accidentally committed to GitHub. Mitigated by adding .env to .gitignore. R7 (Closed) — MySQL reserved keyword "rank" caused LOAD DATA INFILE to fail. Resolved by using Node.js import scripts instead.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | A1 — Students know their entrance exam percentile or rank before using the application. A2 — NIRF rankings are the most credible and widely accepted ranking system for Indian colleges. A3 — Fees data estimated by college type (IIT, NIT, private, state) for colleges imported from the NIRF CSV. A4 — Application runs on a machine with Node.js v20+ and MySQL Server 8.0+ installed. A5 — JoSAA 2025 cutoff data not yet available — 2024 data used as the most recent source. A6 — Modern browsers (Chrome, Edge, Firefox, Safari) are used — localStorage, fetch API and CSS animations supported. A7 — Placement data is available only for colleges with well-documented annual placement reports.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | C1 — Technology: Frontend must use HTML, CSS and JavaScript. Backend must use Node.js. Database must be SQL-based (MySQL). No other frameworks permitted as per project brief. C2 — Timeline: Project must be completed within the IAC internship programme duration (20 May – 25 May 2025). C3 — Resources: Single developer (Shrey). No additional team members or budget available. C4 — Data: 2025 JoSAA cutoff data not available until July 2025. Application limited to 2024 data for cutoffs. C5 — Deployment: Application currently runs locally. Production deployment is out of scope for the current sprint. C6 — Security: No HTTPS or SSL certificate configured. Application not suitable for public internet exposure in current state. C7 — Compatibility: Application must be compatible with Windows, macOS and Linux development environments (Node.js and MySQL are cross-platform).
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 20-May-2025 Requirement Elicitation Questionnaire completed. Project brief reviewed. All requirements documented.
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 21-May-2025 Project Schedule created. RAID Log initialised. Database schema designed. Work breakdown structure defined.
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 22-May-2025 Software Design Specification completed. Database tables created and seeded with 20 colleges. API endpoints designed and documented.
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 23-May-2025 All 4 REST API endpoints built and tested. NIRF CSV imported — 455 colleges in database. Frontend pages (landing, explore, detail, compare) built and connected to API.
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 24-May-2025 Test Plan completed. Traceability Matrix completed with 30 test cases executed. All Priority 1 and 2 bugs resolved and verified.
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 25-May-2025 (Planned) Application deployed to Railway (backend) and Netlify (frontend). Production API URL updated in frontend. Database migrated to Supabase.
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 25-May-2025 All documentation: Coding Standards, Test Plan, RTM, Project Report, Project Schedule, RAID Log, Lessons Learnt, SDS, Requirement Elicitation, Project Charter. Lessons Learnt Log finalised.