## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Shreya Panse
Document Created On: | 2025-05-20
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## Project Schedule
IAC Internship Program 2025 - Web Development Project Schedule
|  | PROJECT START DATE | 2025-05-20 | (Enter the date you started working on your project)
|  | Display Week Sr No | 1 | [10 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | time axis 2025-05-19 to 2025-07-20
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2025-05-19 to 2025-07-20
1 | Sprint 1 – Project Initiation & Planning
1.1 |  | Project Initiation |  |  |  | Shreya Panse | 2025-05-20 | 2025-05-20 | 2025-05-20 | 4 | Completed | 100%
1.1.1 |  | Project Initiation | Define project scope and objectives |  |  | Shreya Panse | 2025-05-20 | 2025-05-20 | 2025-05-20 | 1 | Completed | 100% | Scope initially IT & Mgmt; expanded to Medical/Law/Design/Arts during dev
1.1.2 |  | Project Initiation | Set up project folder & Git repository |  |  | Shreya Panse | 2025-05-20 | 2025-05-20 | 2025-05-20 | 1 | Completed | 100%
1.1.3 |  | Project Initiation | Create .gitignore (node_modules, .env) |  |  | Shreya Panse | 2025-05-20 | 2025-05-20 | 2025-05-20 | 0.5 | Completed | 100% | Security — .env must never be committed; do this at project init
1.2 |  | Project Planning |  |  |  | Shreya Panse | 2025-05-20 | 2025-05-21 | 2025-05-21 | 3 | Completed | 100%
1.2.1 |  | Project Planning | Define database schema |  |  | Shreya Panse | 2025-05-20 | 2025-05-21 | 2025-05-21 | 2 | Completed | 100% | Audit source data fields before schema design
1.2.2 |  | Project Planning | Identify data sources (NIRF primary, Kaggle fallback) |  |  | Shreya Panse | 2025-05-20 | 2025-05-21 | 2025-05-21 | 1 | Completed | 100% | NIRF portal CSV unavailable; Kaggle used as backup source
2 | Sprint 2 – Backend Development
2.1 |  | Server & API Setup |  |  |  | Shreya Panse | 2025-05-20 | 2025-05-22 | 2025-05-22 | 6 | Completed | 100%
2.1.1 |  | Server & API Setup | Initialise Node.js + Express server (server.js) |  |  | Shreya Panse | 2025-05-20 | 2025-05-20 | 2025-05-20 | 1 | Completed | 100%
2.1.2 |  | Server & API Setup | Create routes/colleges.js with separated route file |  |  | Shreya Panse | 2025-05-21 | 2025-05-22 | 2025-05-22 | 2 | Completed | 100% | Specific routes declared before wildcard /:id to avoid interception bug
2.1.3 |  | Server & API Setup | Fix GET /colleges/exams/all route ordering bug |  | 2.1.2 | Shreya Panse | 2025-05-20 | 2025-05-20 | 2025-05-20 | 1 | Completed | 100% | Express: specific routes first, wildcard routes last
2.1.4 |  | Server & API Setup | Add future route stubs (routes/chat.js, routes/users.js) |  | 2.1.2 | Shreya Panse | 2025-05-22 | 2025-05-22 | 2025-05-22 | 0.5 | Completed | 100%
2.2 |  | Database Development |  |  |  | Shreya Panse | 2025-05-21 | 2025-05-23 | 2025-05-23 | 8 | Completed | 100%
2.2.1 |  | Database Development | Create MySQL database and tables |  |  | Shreya Panse | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2 | Completed | 100% | Avoided MySQL reserved keyword "rank"; wrapped in backticks
2.2.2 |  | Database Development | Write Node.js import.js script for bulk CSV import |  | 2.2.1 | Shreya Panse | 2025-05-21 | 2025-05-22 | 2025-05-22 | 3 | Completed | 100% | Imported 354 colleges in <10s with duplicate detection; replaces LOAD DATA INFILE
2.2.3 |  | Database Development | Fix college_courses junction table for domain filter |  | 2.2.2 | Shreya Panse | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2 | Completed | 100% | Medical/Law/Design/Arts colleges must have college_courses records for JOIN filter
2.2.4 |  | Database Development | Source & insert placement data for top 20 seed colleges |  | 2.2.3 | Shreya Panse | 2025-05-23 | 2025-05-23 |  | 1 | In progress | 80% | NIRF CSV lacked fees/placement; estimated by college type
3 | Sprint 3 – Frontend Development
3.1 |  | UI Design & Theming |  |  |  | Shreya Panse | 2025-05-22 | 2025-05-24 | 2025-05-24 | 6 | Completed | 100%
3.1.1 |  | UI Design & Theming | Define CSS custom properties (:root variables) for theming |  |  | Shreya Panse | 2025-05-22 | 2025-05-22 | 2025-05-22 | 1 | Completed | 100% | Dark navy + green accent; CSS keyframe animations with cubic-bezier easing
3.1.2 |  | UI Design & Theming | Build college card components with hover animations |  | 3.1.1 | Shreya Panse | 2025-05-23 | 2025-05-24 | 2025-05-24 | 3 | Completed | 100%
3.1.3 |  | UI Design & Theming | Implement navigation bar and footer |  | 3.1.1 | Shreya Panse | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2 | Completed | 100%
3.2 |  | Core Frontend Features |  |  |  | Shreya Panse | 2025-05-22 | 2025-05-24 | 2025-05-24 | 10 | Completed | 100%
3.2.1 |  | Core Frontend Features | Build explore page: college grid & domain filter chips |  | 2.1.2 | Shreya Panse | 2025-05-22 | 2025-05-23 | 2025-05-23 | 3 | Completed | 100%
3.2.2 |  | Core Frontend Features | Fix filter state persisting across pagination pages |  | 3.2.1 | Shreya Panse | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2 | Completed | 100% | Global currentFilters object; state must live outside async functions
3.2.3 |  | Core Frontend Features | Fix NaN rendering for colleges with missing placement data |  | 3.2.1 | Shreya Panse | 2025-05-23 | 2025-05-23 | 2025-05-23 | 1 | Completed | 100% | Null-safe rendering: c.avg_package_lpa ? value : "—"
3.2.4 |  | Core Frontend Features | Implement compare list with localStorage persistence |  | 3.2.1 | Shreya Panse | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2 | Completed | 100% | compareList as JSON in localStorage; try-catch for disabled browsers
3.2.5 |  | Core Frontend Features | Add advance search bar (keyword + domain filter) |  | 3.2.1 | Shreya Panse | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2 | Completed | 100%
4 | Sprint 4 – Data Collection & Integration
4.1 |  | Data Collection |  |  |  | Shreya Panse | 2025-05-21 | 2025-05-23 | 2025-05-23 | 5 | Completed | 100%
4.1.1 |  | Data Collection | Attempt NIRF portal direct CSV download |  |  | Shreya Panse | 2025-05-21 | 2025-05-21 | 2025-05-21 | 0.5 | Completed | 100% | NIRF removed CSV button; always identify backup source before data collection
4.1.2 |  | Data Collection | Download NIRF 2024 dataset from Kaggle (backup) |  | 4.1.1 | Shreya Panse | 2025-05-21 | 2025-05-21 | 2025-05-21 | 0.5 | Completed | 100%
4.1.3 |  | Data Collection | Audit CSV fields; plan estimation for missing columns |  | 4.1.2 | Shreya Panse | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2 | Completed | 100% | Data audit step added to project planning checklist
4.1.4 |  | Data Collection | Run import.js; validate college_courses links |  | 4.1.3 | Shreya Panse | 2025-05-22 | 2025-05-23 | 2025-05-23 | 2 | Completed | 100% | Run validation query after every import to check for colleges with no course links
5 | Sprint 5 – Testing & Project Closure
5.1 |  | Testing |  |  |  | Shreya Panse | 2025-05-25 | 2025-05-25 | 2025-05-25 | 4 | Completed | 100%
5.1.1 |  | Testing | Write Test Plan and Traceability Matrix |  |  | Shreya Panse | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2 | Completed | 100% | Test plan to be written before frontend dev in future sprints
5.1.2 |  | Testing | Manual end-to-end testing of all features |  | 5.1.1 | Shreya Panse | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2 | Completed | 100%
5.2 |  | Project Closure |  |  |  | Shreya Panse | 2025-05-25 | 2025-05-25 | 2025-05-25 | 3 | Completed | 100%
5.2.1 |  | Project Closure | Complete Lessons Learnt Log (15 entries) |  |  | Shreya Panse | 2025-05-25 | 2025-05-25 | 2025-05-25 | 1 | Completed | 100% | Agile retrospective; backend-first sprint order confirmed as best practice
5.2.2 |  | Project Closure | Document scope change in Project Report |  |  | Shreya Panse | 2025-05-25 | 2025-05-25 | 2025-05-25 | 0.5 | Completed | 100%
5.2.3 |  | Project Closure | Plan future sprints: chatbot API & user accounts |  | 5.2.2 | Shreya Panse | 2025-05-25 | 2025-05-25 |  | 1 | Not Started | 0% | Build /chat API first, then chat widget UI (backend-first approach)
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you

## EXAMPLE
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Job Cloud |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE
PROJECT START DATE | 2020-01-01
PROJECT END DATE | 2020-01-04
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.2 Recruit a team |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.3 Create a project charter |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.2 Baseline project plan |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2020-12-01 | 20/1/2020 | 8 | COMPLETED
| 3.2 Build |  | 22/1/2020 | 22/3/2020 | 59 | IN PROGRESS
| 3.2.1 Features |  | 22/1/2020 | 31/1/2020 | 9
Registration of candidate and employer
Login for candidate and employer
| Home page layout |  | 2020-01-02 | 2020-10-02 | 10
Navigation bar with logo
Home
Jobs
| Candidates |  | 2020-11-02 | 15/2/2020 | 5
List of candidates with information
| Employer |  | 16/2/2020 | 21/2/2020 | 5
List of employers with information
Advance search bar
Keyoword
Upload resume
Job categories
| Job listing/ Job result page |  | 22/2/2020 | 26/2/2020 | 4
Employer name
Job category & type information
Date & location
Favorite
Apply filter & sort
| Apply for job/ Jobs tag |  | 26/2/2020 | 29/2/2020 | 3
Employer information
Deadline of application
Job details
Job description
Role
Required skills
| Footer |  | 2020-01-03 | 2020-09-03 | 8
Quick links for candidate & employer
Legal and company information
Social media follow
| Profile |  | 2020-10-03 | 15/3/2020 | 5
Dashboard
Job alerts
Applied jobs/Posted jobs
Favorite jobs/candidates
Basic information of candidate/employer
| Post job |  | 16/3/2020 | 22/3/2020 | 7
Job title and desciption
Job category and type
Required skills and application deadline
Salary and qualification
Location
| 3.3 Testing |  | 25/03/2020 | 31/3/2020 | 6
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure |  | 2020-01-04 | 2020-01-04 | 1