## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 6 | 0 | 2 | 2 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | CollegeCompass — College Finder Web Application |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 4 | 0 | 0 | 1 | 3 | 0
[10 empty] | Issue | 5 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | v1.0 |  | Last Updated date: | 25-May-2025 | Project Team Lead: | Shreya Panse |  |  | Dependency | 5 | 0 | 1 | 2 | 2 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 20 |  |  |  |  | 13
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | JoSAA 2025 cutoff data not yet available. Current database contains only 2024 cutoffs. | Students searching for 2025 admissions may see outdated cutoff information leading to incorrect college shortlisting. | Display a clear disclaimer on all cutoff data stating "Based on 2024 data". Build the import_cutoffs.js script so data can be updated with one command as soon as JoSAA 2025 data is released in July 2025. | Shrey | High | 6 | Open
2 | Risk | Only 62 out of 455 colleges have verified placement data. Remaining colleges show blank placement fields. | Students comparing colleges without placement data may not get a complete picture. This could reduce trust in the platform. | Mark cards clearly with "Placement data unavailable" instead of showing empty fields. Prioritise sourcing placement data from official college annual reports for the top 100 NIRF-ranked colleges in future sprints. | Shrey | Moderate | 4 | Open
3 | Risk | Backend server runs locally on localhost:3000 and is not deployed to a live server. | The application cannot be accessed by anyone outside the development machine. It cannot be demonstrated to stakeholders without running the server locally. | Deploy backend to Railway (free tier) and frontend to Netlify. Database to be migrated to Supabase or Railway PostgreSQL. Deployment planned as a post-documentation sprint. | Shrey | High | 6 | Open | Issue
4 | Risk | No input validation or rate limiting on API endpoints. Any user can send malformed requests or flood the server. | Malformed requests could cause server crashes. Without rate limiting the API could be overwhelmed. | Add express-validator middleware for input sanitisation on all routes. Add express-rate-limit package to restrict requests to 100 per 15 minutes per IP. Planned for production deployment sprint. | Shrey | Moderate | 3 | Open | Dependency
5 | Risk | Database credentials stored in .env file which could accidentally be committed to GitHub. | Exposing DB_PASSWORD and DB_HOST publicly could allow unauthorised database access. | .env file added to .gitignore before any GitHub push. Verified .env is not tracked by Git. For production, credentials to be stored as environment variables in Railway dashboard. | Shrey | High | 5 | Closed
6 | Risk | MySQL AUTO_INCREMENT IDs could conflict if the database is reset and re-seeded multiple times during development. | Duplicate primary key errors could cause import scripts to fail mid-run. | Import scripts use INSERT IGNORE to skip duplicates. Unique constraints on college name field prevent duplicate entries. import.js checks for existing records before inserting. | Shrey | Low | 2 | Closed | Open
7 | Assumption | Students using CollegeCompass are assumed to have already appeared for their entrance exam and know their percentile or rank. | If students do not know their score the percentile filter cannot be used effectively reducing the core value of the application. | Add tooltip help text next to the percentile input explaining how to find their JEE Main percentile from the official NTA scorecard. Consider adding a rank-to-percentile converter tool in a future sprint. | Shrey | Low |  | Open | Closed
8 | Assumption | NIRF rankings are assumed to be the most credible and widely accepted ranking system for Indian colleges. | Some students may prefer QS World Rankings or NAAC grades. Relying solely on NIRF may not satisfy all user preferences. | NIRF ranks are displayed as the primary sort order. Future sprints can add QS rank and NAAC grade as additional data columns sourced from official websites. | Shrey | Low |  | Open
9 | Assumption | Fees data for colleges imported from the NIRF CSV has been estimated by college type (IIT NIT private state) since the NIRF dataset does not include fee information. | Estimated fees may not match actual fees charged by specific colleges leading to inaccurate information for students. | Fees for the 20 manually seeded colleges were verified from official college websites. A disclaimer is included noting fees are approximate. Real fee data to be sourced and updated in a future data refresh sprint. | Shrey | Moderate |  | Open | Critical
10 | Assumption | The application is assumed to run on a machine with Node.js v20+ and MySQL 8.0+ installed. No containerisation (Docker) is used. | If a different environment is used the application may not run correctly due to version incompatibilities. | All dependency versions are locked in package-lock.json. README to document exact Node.js and MySQL version requirements. Docker containerisation planned as a future enhancement. | Shrey | Low |  | Open | High
11 | Issue | Route ordering bug — GET /colleges/exams/all was being matched by the /:id wildcard route returning a "college not found" error instead of the exams list. | The /colleges/exams/all endpoint returned an error. Exam chips on the frontend could not load causing the explore page to show no exam filter options. | Resolved by moving the /exams/all route declaration above the /:id route in colleges.js. Express matches routes in declaration order so specific routes must always precede wildcard routes. | Shrey | High |  | Closed | Moderate
12 | Issue | Medical domain filter returned 0 results despite 13 medical colleges being present in the colleges table. | Students selecting the Medical domain filter saw an empty college grid. The filter appeared broken. | Root cause was missing college_courses junction table records. Medical colleges were inserted into the colleges table but not linked to the MBBS course in college_courses. Fixed by running INSERT statements to link all medical colleges to their courses. | Shrey | High |  | Closed | Low
13 | Issue | Pagination was resetting all applied filters when navigating between pages. | A student who filtered by JEE Main exam and clicked to page 2 would see unfiltered results losing their filter selection. | Fixed by storing the current filter state in a global currentFilters object in JavaScript. The changePage() function now passes currentFilters to loadColleges() on every page change ensuring filters persist across pages. | Shrey | Moderate |  | Closed | Negligible
14 | Issue | LOAD DATA INFILE SQL command failed with Error Code 1064 when attempting to import JoSAA CSV directly in MySQL Workbench. The word "rank" is a reserved keyword in MySQL. | Direct SQL import of the JoSAA CSV was blocked. Data could not be imported through MySQL Workbench. | Replaced the MySQL LOAD DATA INFILE approach with a custom Node.js import script (import.js) that reads the CSV using the fs module and inserts records via parameterised queries. This approach is safer and more flexible. | Shrey | High |  | Closed
15 | Issue | College cards showing package data as NaN or undefined for colleges imported from NIRF CSV which have no placement records. | College cards showed broken "₹NaNL" text in the Avg. Package stat instead of a clean dash. | Fixed by adding null-safe checks in the renderColleges() function. All stat values now use conditional rendering: c.avg_package_lpa ? value : "—". Empty values display a clean dash instead of undefined. | Shrey | Low |  | Closed
16 | Dependency | Frontend fetch calls depend on the Node.js backend server running on localhost:3000. If the server is not running all API calls fail and the explore page shows an error state. | Any developer or evaluator must start the backend server before opening the frontend. Forgetting to run node server.js results in a broken application. | Add clear startup instructions to README.md. Add a connection health check that shows a user-friendly "Server offline" message in the UI instead of a raw fetch error. Deployment to Railway will eliminate this dependency for end users. | Shrey | High |  | Open
17 | Dependency | The college domain filter depends on records existing in the college_courses junction table. Colleges without course links do not appear in domain-filtered results even if they are the correct domain. | New colleges added to the colleges table without corresponding college_courses records will be invisible to domain filters. | Document the college_courses insertion step in the data import workflow. Add a validation query to import scripts that checks for colleges with no course links and logs a warning. Future import scripts to auto-link colleges to courses based on the domain field. | Shrey | Moderate |  | Open
18 | Dependency | Cutoff prediction feature (planned) depends on having at least 3 years of historical cutoff data per college. Currently only 2024 cutoff data exists for 62 colleges. | The cutoff prediction sprint cannot begin until multi-year JoSAA CSV data is sourced and imported. This blocks a key planned feature. | Source 2022 and 2023 JoSAA cutoff CSVs from Kaggle. Write import_cutoffs.js to handle the JoSAA CSV format. Once 3 years of data are available the linear regression prediction model can be built in Node.js. | Shrey | Moderate |  | Open
19 | Dependency | AI chatbot feature (planned) depends on obtaining an Anthropic API key and available API credits. | Without API credits the chatbot cannot make calls to the Claude API. This blocks the most prominent planned feature. | Register for an Anthropic account at console.anthropic.com to obtain free trial credits. Store the API key in the .env file as ANTHROPIC_API_KEY. Build the chatbot only after API access is confirmed. | Shrey | Low |  | Open
20 | Dependency | The compare feature depends on localStorage being available in the browser. The compareList is stored in localStorage to persist selections across pages. | If a browser has localStorage disabled or if the user is in private/incognito mode the compareList will not persist between pages and the compare feature will not work correctly. | Add a try-catch around all localStorage operations with a fallback to an in-memory array. Display a warning banner if localStorage is unavailable. This is a minor edge case affecting very few users. | Shrey | Low |  | Open
21
22
23
24